## Backlog Tracker
Apex Flight Hub — Backlog Tracker
Line numbers match Riaan's 28 Sep 2026 renumbering. Batch column shows which delivered batch (script) covers each line -- "—" means not built yet or predates batch numbering.
Line No. | Batch | Description | Date Implemented | Comments | Action Required | comments Latest
V22 · 23 Sept 2026
51 | — | CFI page, Manage Syllabus — must be able to EDIT an exercise, not only remove it. | Confirmed live 28 Sep 2026 | Riaan confirmed: Done, Working. (Predates batch numbering.) | None.
52 | — | Add to Students/Pilots (all roles): a new "Forms and procedures" tab on the top menu. Inside it, a list of empty slots (10 + "add more") where a CFI/Admin can upload a pic, PDF, PowerPoint or zip file for download. | Confirmed live 28 Sep 2026 | Riaan confirmed: Done, Working. (Predates batch numbering.) | None.
53 | — | Hovering over a menu item should turn it RED and larger. | Confirmed live 28 Sep 2026 | Riaan confirmed: Done, Working. (Predates batch numbering.) | None.
54 | — | Under Pilot — still to be developed: (a) sign-off/renewal section of licence with document autocomplete of forms and submission (marked TBA by Riaan); (b) "Select" (incomplete note). |  | This is the renewal-time CFI review + SACAA document pack — the item explicitly parked, not scoped, do-not-build-without-asking. No comment from Riaan on the tracker (stays parked). | Stay parked until Riaan scopes it. | will tart soon
55 | — | On the pilot/student page, add a "View profile" button — the Edit profile button already exists. | Confirmed live 28 Sep 2026 | Riaan confirmed: Done, Working. (Predates batch numbering.) | None.
56 | — | Under Profile: printable version AND a proper view (currently only Edit + Print — add a real View). Should show: (i) total flights summary (with an editable starting count/history), (ii) total hours summary (with editable starting hours), (iii) summary of the last 12 months since licence renewal, (iv) summary of hours in that same 12 months. | Confirmed live 28 Sep 2026 | Riaan confirmed: Done, Working. (Predates batch numbering.) | None.
57 | — | On the Logbook page, just above the flight list (under the CSV import), add a summary line: (a) total flights since a settable start number, (b) total flight hours since a settable start point, (c) total flights in the last 12 months since renewal, (d) total hours since last renewal. | Confirmed live 28 Sep 2026 | Riaan confirmed: Done, Working. (Predates batch numbering.) | None.
V23 · 25 Sept 2026
60 | — | Stray note at the top of the list: "A personal document library is still coming in a later build stage. This page covers your account, verified endorsements, and the ratings ladder." |  | Riaan's answer: "stand by." | On hold — revisit later, not urgent.
61 | 36, 38 | On the pilot screen, under "Apply for": Paraglider / Powered Paraglider / Paratrike, each with Intermediate / Sport / Tandem options. | 28 Sep 2026 (batch 36 v1) / 28 Sep 2026 (batch 38 fix, deployed & confirmed live) | Batch 36's first cut only showed a tier when the pilot had ZERO endorsements in that whole equipment type. Riaan tested live and found PG/PPG (both already holding Basic) still showed nothing under "Apply for something else" for Intermediate/Sport/Tandem. Root cause: the ladder's own Apply button is separately gated by CAR Part 106 time-in-rank eligibility, so a freshly-Basic pilot had no Apply option anywhere. Batch 38 fixed it: any not-yet-held tier now shows under "Apply for something else" regardless of engagement or eligibility. Confirmed deployed via a live Railway check. | None — deployed and confirmed. Worth one visual glance on your live site.
62 | — | Clicking an unearned rating (not the green ticked one) opens an overlay with that rating's requirements/exercises/docs/references, plus an "add more subsections" button. Clicking Apply opens an upload flow (CAR106/CAT106/Apex MOP docs) instead of just turning the badge yellow, then submits for CFI verification. |  | Riaan's answer: no separate content editor — CFI adds picture/note/doc directly via an "Add+" button. Needs one new shared database table (with item 70 below), but there's no existing CFI-facing screen to attach an Add+ button to for rating content specifically (unlike item 70, which fits into the existing Manage Syllabus editor). | Not started — proposing a CFI-screen approach to Riaan before building. | 2026-10-13 17:20
63 | 35 | When applying/signing up and uploading a CAA licence, there must be a field for the correct "date first issued" (editable by CFI on verification) — NOT the upload date. Critical so existing pilots with years of hours/flights carry over cleanly into the new system. | 25 Sep 2026 (built) / 28 Sep 2026 (deployed) | Delivered in batch 35. Field added to sign-up, pilot's own Edit profile, and the CFI/Admin applicant page. | Riaan: confirm it's showing correctly on your live site.
64 | 36 | When uploading any document (same as Signature), add a View button next to the upload so the pilot can confirm the correct doc was uploaded. Student and pilot must be able to view an uploaded doc, including from their profile. | 28 Sep 2026 (built & deployed, confirmed live) | Delivered in batch 36 — Riaan said "pls build." Added "View current copy" links next to the flight medical certificate and CAA licence uploads on the pilot/student's own Edit profile page. The CFI/Admin review page already had View links for every document from an earlier batch. Riaan confirmed working as intended. | None — done.
65 | 35 | Pilot or Student must be able to reset their password without Admin/CFI approval. The reset link must be emailed to them. | 25 Sep 2026 (built) / 28 Sep 2026 (deployed, confirmed live via Railway) | Delivered in batch 35 — real emailed reset link (1 hour validity) via Resend. Old CFI/Admin-mediated queue kept as a fallback if the email can't be sent. | Riaan: confirm it's working on your live site — deployment confirmed, actual behaviour not yet visually checked.
66 | 35 | CFI or Instructor must be able to edit or delete a student's flight log entry. | 25 Sep 2026 (built) / 28 Sep 2026 (deployed, confirmed live via Railway) | Delivered in batch 35 — added to the existing per-student logbook review page. Editing never changes the entry's verified status. | Riaan: confirm it's showing correctly on your live site — deployment confirmed, actual behaviour not yet visually checked.
67 | 35 | A Pilot must be able to sign off, edit, or delete their own flight log entry. | 25 Sep 2026 (built) / 28 Sep 2026 (deployed, confirmed live via Railway) | Delivered in batch 35 — Edit/Delete buttons on every entry on /pilot/logbook. | Riaan: confirm it's showing correctly on your live site — deployment confirmed, actual behaviour not yet visually checked.
68 | 35 | A pilot's flight log entry is self-signed the moment the pilot enters it — no CFI/Instructor review needed. | 25 Sep 2026 (built) / 28 Sep 2026 (deployed, confirmed live via Railway) | Delivered in batch 35 — entries insert as self-signed for pilot-role users (and CSV import). Existing pending pilot entries were retroactively self-signed by migration. | Riaan: confirm it's showing correctly on your live site — deployment confirmed, actual behaviour not yet visually checked.
69 | 35 | Instructor ONLY reviews and signs off the Student logbook (not the pilot logbook). | 25 Sep 2026 (built) / 28 Sep 2026 (deployed, confirmed live via Railway) | Delivered in batch 35 — the flip side of item 68; student entries are unaffected and still require CFI/Instructor countersign exactly as before. | Riaan: confirm it's showing correctly on your live site — deployment confirmed, actual behaviour not yet visually checked.
70 | 51 | "Big one" — on a student's training folio, exercises need an info button next to sign-off that opens an overlay showing the exercise's sub-sections (sub-exercises, docs, pictures), with an "add more sub-sections" button for the CFI. | 1 Oct 2026 (batch 51 — deployed & confirmed live on Railway) | Info button (i + count) next to each exercise on the student folio (only where content exists), the CFI student folio next to sign-off, and Manage Syllabus. Opens an overlay of sub-sections: title + note, picture (shown in the overlay), document (download) or link (for videos/big files). CFI gets Add+ and Remove inside the overlay; students and regular instructors read only. Files max 25MB; pictures need a sign-in to view. New shared content_items table, built so line 62's rating content can reuse it. Deleting an exercise/section removes its sub-sections. Tested end to end (15 checks). | Live. Open an exercise's i button in Manage Syllabus and Add+ a sub-section.
71 | 35 | Pilot Logbook (not Student logbook) redesign: flight type PG/PPG/PPT, and the "Exercises Covered" list replaced/renamed "Flight Task": Solo, XC, Tandem, Tandem Flight Instruction (TFI), Skill test, Renewal, Equipment test, Display. | 25 Sep 2026 (built) / 28 Sep 2026 (deployed, confirmed live via Railway) | Delivered in batch 35. The PG/PPG/PPT flight-type field already existed and needed no change; the checklist itself was replaced on the pilot side only — student logbook is unchanged. | Riaan: confirm it's showing correctly on your live site — deployment confirmed, actual behaviour not yet visually checked.
V24 (new — paste appears incomplete)
73 | 36 | On the Instructor/CFI review page: for a student-uploaded exam, the Instructor must be able to (a) delete the exam and/or upload a new one, (b) mark pass/fail correctly, (c) next to "View what was submitted": Delete or new upload. | 28 Sep 2026 (built & deployed, confirmed live) | Delivered in batch 36 — Riaan said "yes." Delete and New upload buttons added next to "View what was submitted" on a paper-exam review. Replacing the file on an already-verified attempt resets it to awaiting review. Mark pass/fail already existed. Riaan confirmed working as intended. Riaan's paste cut off mid-item — may be more to V24. | Paste the rest of V24 if there's more.
V24 continued, line 71 onwards · logged 30 Sept 2026, built 1 Oct 2026 (batch 50, live)
71 | 50 | Student sign-up form redesign: "What type(s) of training are you signing up for" becomes a genuine multi-select (Paraglider and/or Powered Paraglider and/or Powered Paratrike) instead of a single choice -- a student can sign up for one or all three. | 1 Oct 2026 (batch 50 — deployed & confirmed live on Railway; batch 51 on top also live) | Sign-up now shows three tick boxes (PG / PPG / PPT); at least one is required; saved as the student's training type(s). Tested with PG + PPT. | Live. Try a test sign-up.
72 | 50 | New field on the sign-up form, under Training: "Initial student sign-up date" -- for backdating students who joined before this system existed. | 1 Oct 2026 (batch 50 — deployed & confirmed live on Railway; batch 51 on top also live) | Optional date under the training tick boxes, for students who started before the Hub (can't be in the future). Saved to the same sign-up date the CFI/Admin edits on the folio and profile (batch 45). | Live. Check it on your site.
73 | 50 | Redesign of the signed-in student's own dashboard header: show only their selected training type(s) under the name/welcome banner; a new line for SACAA No., SAHPA No., SAHPA Expiry date (moved off the top line, CFI/Admin-editable), Apex No. and Call Sign; the top welcome line's "Expiry date" replaced with "Initial student sign-up date" (CFI/Admin-editable). "Red Flight log bar, Correct". | 1 Oct 2026 (batch 50 — deployed & confirmed live on Railway; batch 51 on top also live) | Welcome line, then Training (selected types only), exercises count and buttons; on the right: Initial student sign-up date. Next line: SACAA No. / SAHPA No. / SAHPA expiry date (red when expired) / Apex No. / Call Sign. Students can't edit either date; CFI/Admin can (folio editor, profile page). Red "+ Log a flight" bar left as is. | Live. Check it on your site.
74 | 50 | Exams on the student dashboard only for the student's training type(s) (PG -> PG; PPG -> PG + PPG + DTO Radio; PPT -> PG + PPT (under construction) + DTO Radio; union if several). Study Notes column next to the exams (one per exam), a Study Notes link in the top menu next to Forms & procedures, and a 1-4 box selector on the CFI's Study material page. | 1 Oct 2026 (batch 50 — deployed & confirmed live on Railway; batch 51 on top also live) | Dashboard now shows one row per exam in Riaan's order (Basic Licence PG, PPG, DTO Radio, PPT) with that box's study note beside it; PPT shows "Under construction". Box 1-4 is tied to the exam (1 PG, 2 PPG, 3 DTO Radio, 4 PPT), so a note stays next to its exam even when other exams are hidden. New Study Notes page in the student menu lists all notes (hiding ones for exams the student can't see). CFI picks the box per item on Study material. Mobile: each exam followed by its note. | Live. Set a dashboard box on your study notes.
75 | 50, 52 | Manage Syllabus: each section gets two dropdowns -- training type (PG / PPG / PPT / Applicable to all) and phase (Phase 1 / 2 / 3 / Conversion (CV) / Practical Theory (PT)). Default exercise codes "Section [PG/PPG/PPT] - P[1/2/3] or CV or PT - Ex[No]/[name]". | 1 Oct 2026 (batch 50 — deployed & confirmed live on Railway; batch 51 on top also live) | Both dropdowns on every section and on Add section; sections grouped by training type, then phase. New exercises get a default code like PPG-P1-Ex8 (editable) and show as "PPG-P1-Ex8 / Straight glide"; existing codes kept. Existing 5 sections tagged PPG, phases 1/1/2/3/3 (Riaan's choice). Up/down arrows move within the same type + phase. | Live. Check the tags on your sections.
76 | 50, 52 | CFI viewing a student's exercises: only sections for that student's training type(s), ordered Phase 1 -> 2 -> 3 -> Conversion. | 1 Oct 2026 (batch 50 — deployed & confirmed live on Railway; batch 51 on top also live) | CFI student folio shows only the student's training type(s) plus "Applicable to all" sections, grouped by type, Phase 1 -> 2 -> 3 -> Conversion -> PT, with phase labels. Unlocking runs within each training type. Empty sections (no exercises) are hidden so they can't lock everything after them. Roster x/y counts only the student's sections. | Live. Check students recorded as PG only -- they won't see PPG sections.
77 | 50, 52 | Student's own progress bar (dashboard) and "View full folio" filtered to the student's training type(s) and phases (e.g. PG + PPG -> PG phases and PPG phases), expanded under View full folio. | 1 Oct 2026 (batch 50 — deployed & confirmed live on Railway; batch 51 on top also live) | Dashboard progress and full folio grouped by training type with phase labels, in phase order, only the student's own training (everything if no type set yet). Message shown if no sections exist for their type yet. | Live. Check it on your site.
Other requests (not on the numbered list) · 28 Sept 2026
— | 37 | Student portal notification bar: one-line orange bar just under the header on every student page. CFI types a message, adds an optional renameable button (linking to an uploaded doc or a web address), and a show/hide switch. | 28 Sep 2026 (batch 37, deployed & confirmed live) | Managed from Instructor → Settings → "Student portal notification bar." Uploading a file and setting a link are mutually exclusive — whichever was set most recently wins. | None — done.
— | 39 | Notification bar resize/centering: "make it shorter, same length as the log book bar, and center the text and button from center outwards." | 28 Sep 2026 (batch 39, built & deployed, confirmed live) | Bar was stretching edge-to-edge across the full browser width; now boxed to the same content-column width as the rest of the page (e.g. the logbook card), with rounded corners. Message + button now centered together as one group. | None — deployed. Worth a glance next time you're on the student side.
— | 40 | MAJOR bug: pilot submits a renewed CAA licence from the expired-licence lock screen, sees "Submitted," but nothing anywhere ever surfaced it for CFI/Admin review — no queue, no flag. | 28 Sep 2026 (batch 40, built & deployed, confirmed live) | Fixed: Instructor/Admin → Pilots now flags any pilot with an unreviewed renewal in red ("New licence submitted <date> -- needs review"), rolling into that page's banner and the Pilots nav badge. Opening the pilot's profile shows the same flag next to their CAA licence document. Saving a new expiry date automatically clears the flag. | Riaan is actively re-testing this flow now (John Doe test pilot).
— | — | Small UX gap found while testing the above: on a pilot's admin profile, the form with the Licence expiry date field starts collapsed behind an "Edit details & documents" button, which is what made Riaan think there was nowhere to set the date. |  | Claude offered to make that form auto-expand (or highlight itself) whenever a pilot has an unreviewed licence renewal, so the next CFI/Admin doesn't hit the same dead end. | Awaiting Riaan's yes/no. YES! | Claude offered to make that form auto-expand (or highlight itself) whenever a pilot has an unreviewed licence renewal, so the next CFI/Admin doesn't hit the same dead end.
— | 41 | MAJOR bug: the ratings-ladder green tiles (e.g. Gary Bowes' PG Basic / PPG Basic) show the wrong "Held since" date. Riaan: must be CFI-editable, and should correspond with the pilot's "Licence first issued" date. | 29 Sep 2026 (batch 41, deployed & confirmed live on Railway) | Root cause: verifying a tier always stamped "held since" to the moment a CFI clicked Verify, not to when the pilot actually held it -- also throws off the next tier's CAR Part 106 eligibility countdown, not just the display. Fixed: verifying Basic now defaults to the pilot's "Licence first issued" date when set (instead of today); every tier now has an "Edit date" link under Verify/Un-verify so any date can be corrected by hand. Deliberately does NOT auto-backdate pilots already verified with the wrong date -- that still needs a manual "Edit date" fix per pilot. | Live now: manually fix Gary Bowes' PG Basic + PPG Basic dates via "Edit date," and check for other pilots in the same boat. | if fix mark green
— | 42 | Bug: on the Pilots list (desktop table), the "Pending" column was showing each pilot's licence-expiry date/status, and the "Licence" column was showing the pending-review badge instead — columns crossed (e.g. Gary Bowes showed "29 May 2027" under Pending). | 29 Sep 2026 (batch 42, deployed & confirmed live on Railway) | Root cause: the desktop table's two <td> cells were written in the wrong order relative to their <th> headers (a copy/paste slip) -- the mobile card view was unaffected. Fixed by putting the pending-count badge and the licence-status cell back in the order matching the headers. | None — done.
— | 43 -> 45 | Student sign-up date: under Students, the only date shown was the app account's creation date (labelled "submitted"), but some students actually joined/signed up close to a year before their account existed. Riaan asked for a CFI/Admin-settable "initial sign-up" date, also shown on the student's application/profile page. | 30 Sep 2026 (batch 43 -> folded into batch 45, deployed & confirmed live on Railway) | Added a new, separate "sign-up date" field (student_profiles.sign_up_date) distinct from both the account's createdAt and the existing training "Start date." Editable by the CFI from the student's folio page, and by CFI or Admin from the student's application/profile page (new "Set date"/"Edit date" control next to "submitted <date>"). Until set for a given student it still falls back to showing the account creation date, marked "not yet confirmed." | Riaan: confirm the "Set date" control shows on a student's folio/application page, then go through existing students and set their real sign-up dates where known.
— | 44 -> 45 | Bug: study material the CFI uploaded (Instructor -> Study material) never appeared for students -- only Forms & procedures showed. Screenshot showed 3 slots stuck on "Saving..." indefinitely after picking large .pptx slide decks. Turned out the file itself was ~330MB (Riaan confirmed from Windows Explorer) -- Riaan's own call: he'll host large files in the cloud himself and just needs a hyperlink/download option here. | 30 Sep 2026 (batch 44 raised the upload cap to 60MB; superseded/folded into batch 45, which adds the link option instead — deployed & confirmed live on Railway) | Root cause of the original hang: next.config.ts capped server-action uploads at 25MB while the page itself advertised 50MB, so anything over 25MB was silently cut off before the save action ever ran (batch 44). But the actual file is ~330MB either way -- far past any sane upload cap. Batch 45 adds a proper link-instead-of-upload option per slot (paste a Google Drive/OneDrive/YouTube link; mutually exclusive with an uploaded file, same pattern as the student notice bar), plus a client-side size check so an over-50MB file now fails instantly with a clear message instead of hanging. | Riaan: confirm the "Link instead" field shows on Study material, then for the 3 stuck slots either re-upload a compressed version or paste a cloud link instead.
— | 46 -> 48 | NEW (30 Sep 2026): automated WhatsApp invites via Riaan's existing Green-API account. CFI/Admin presses an "Invite via WhatsApp" button, enters the person's name and phone number, and the portal sends a WhatsApp invite automatically. Plus (Riaan, same day): an "Invites" block under Pilots listing who was invited, with a Re-invite link next to each name, and the name removed once that person signs up. Riaan's example text: "Hi John, team Apex invite you to join our Apex Flight Hub ... sign up via the link ... regards, Riaan, Team Apex" | 30 Sep 2026 (batch 46, then included in batch 48 — deployed & confirmed live on Railway) | Pilots page now has an Invites block (CFI and Admin): "+ Invite via WhatsApp" opens name, cell number and a pre-filled message that follows the name typed (editable before sending); Re-invite resends the same message; Remove takes a name off by hand. A name drops off automatically once anyone signs up with the same cell number. SA numbers 0XX... become 27XX...; a number already invited or already belonging to a member is refused; a failed send is kept with its reason so it can be retried. Default message is Riaan's text with spelling tidied and the link pointing straight to /signup. Tested end to end (17 checks) against a stand-in Green-API server. | Variables added in Railway. Check the orange "not connected" note is gone on Pilots -> Invites, then send a test invite to your own number.
— | 47 -> 48 | NEW (30 Sep 2026, flagged very important): under the Admin page add Students, so Admin (and CFI) can check and view student profiles and edit profile details. Riaan: "As CFI or Admin we can not view a student's profile, make changes or print it!" | 30 Sep 2026 (batch 47, then included in batch 48 — deployed & confirmed live on Railway) | New Admin -> Students page (CFI and Admin): every approved student with training, Apex No., cell, signed-up date, SAHPA expiry (red when expired) and status, plus View / edit and Print per row. The profile page gained a Print profile button and a Student details section (call sign, SACAA No., SAHPA No., SAHPA expiry, training start date); its Edit details form now edits those four student fields too (previously only the CFI folio could). New printable profile sheet (personal, next of kin & medical, student/pilot details, consent & documents on file, flying summary and exercise progress). The CFI's student folio got Full profile (view / edit) and Print profile links (CFI only; regular instructors can't open Admin pages). Tested end to end (20 checks); caught and fixed a column mix-up in the first cut of the list. | Open Students, pick a student, and try Edit details and Print profile.
— | 48 | NEW (30 Sep 2026): WhatsApp invite button for students, same as for pilots -- logged, and removed once they sign up. Riaan's message: "Hi John, Please sign up as student to Team Apex, use the link ... to sign in as student. Please provide all details and upload necessary doc to get validated and approved. The Hub will give you access to all your exams, training doc etc. As soon as verified you will receive a WhatsApp to confirm. Regards, Riaan, Team Apex" | 30 Sep 2026 (batch 48, deployed & confirmed live on Railway) | Students page now has its own Student invites block: "+ Invite student via WhatsApp" with Riaan's student message pre-filled (spelling tidied, link to /signup, editable), Re-invite and Remove, and the name drops off once they sign up with that cell number. Pilot and student invites are kept on separate lists; a number already invited on either list is refused with a note saying which page it's on. Tested end to end. | Send a test student invite to your own number.
— | 48 | NEW (30 Sep 2026): as soon as a CFI or Admin verifies and approves a student's application, the student must receive a WhatsApp saying they can now log in. Same for pilots. (Riaan asked whether this is possible -- yes.) | 30 Sep 2026 (batch 48, deployed & confirmed live on Railway) | Approving a pending student or pilot now sends them a WhatsApp: "Hi John, good news! Your Apex Flight Hub student [or pilot] application has been verified and approved. You can now log in here: .../login Regards, Riaan, Team Apex". Uses the cell number from their sign-up. The approval always goes through; the verification queue then shows a banner saying whether the WhatsApp was sent, failed, or couldn't be sent (no number / WhatsApp not connected). The approve panel warns that a WhatsApp will go out. Tested end to end against a stand-in Green-API server. | Approve a test sign-up and check the WhatsApp arrives. Say if the wording should change.
— | 49 -> 50 | Follow-up (30 Sep 2026): Riaan couldn't see batch 48's Student invites. They were only on Admin -> Students; the CFI's own "Students" menu item opens the training roster instead, which had no invites. | 30 Sep 2026 (batch 49, included in batch 50 — deployed & confirmed live on Railway) | Student invites block now also at the bottom of the CFI's Students roster (/instructor), CFI only (regular instructors don't see it); same list as Admin -> Students. CFI menu gets a "Student profiles" link to Admin -> Students (view / edit / print). Tested end to end. | Live. Check the Student invites block at the bottom of your Students page.
— | 52 | Follow-up (1 Oct 2026, Riaan's screenshot of the live Training folio): "the order of the folio is wrong. Phase 1 first, then phase 2, then phase 3, then the rest." Batch 50 ordered sections by training type first (all "Applicable to all" sections, then PG, PPG, PPT) and only then by phase, so a General Phase 3 showed before a PPG Phase 2. | 1 Oct 2026 (batch 52, built & delivered — not yet run) | All folio views (student folio + dashboard progress, CFI student folio, Manage Syllabus) now run phase first: Phase 1 -> 2 -> 3 -> Conversion -> Practical Theory, headed by phase, with a small badge on each section (All types / PG / PPG / PPT). Unlocking follows the same order. Migration 0038 gives sections named "Phase 1/2/3 ..." the matching phase tag (fixes a "Phase 2 - ..." section still on the default Phase 1). Tested (8 checks) plus the 71-77 and line 70 tests re-run green. | Run batch 52, then check the Training folio order. If a section is still in the wrong phase, fix its Phase dropdown in Manage Syllabus.
— | 53 | MAJOR (6 Oct 2026, Riaan's screenshot): saving a ~20MB document under Study material crashed the page ("This page couldn't load -- a server error occurred"). | 6 Oct 2026 (batch 53, also inside batch 54 — pushed 8 Oct 2026 (commit 98c5ed4), awaiting Railway ACTIVE) | Cause: the site's sign-in check (proxy) only passes the first 10MB of a form upload on to the save action; anything bigger arrived cut short and the save crashed. Raised that limit to 60MB (same as the upload limit already set). Also fixes the same crash for Forms & procedures, exercise sub-sections and sign-up documents over 10MB. Reproduced (20MB crashed) and fixed: small, link, 20MB and 40MB saves all work. | Run batch 53 (or 54, which includes it), then save the 20MB study note again. | if fix mark green
— | 54 | Request (8 Oct 2026): on a student's submitted paper exam / radio licence the CFI only had "View what was submitted, New upload, Delete" -- add a way to download it too. | 8 Oct 2026 (batch 54, built & delivered — pushed 8 Oct 2026 (commit 98c5ed4), awaiting Railway ACTIVE) | New Download button next to "View what was submitted" on the CFI's exam review page; saves as "<Student name> - <Exam title>.pdf". Also a Download link next to View on every document on a student's/pilot's profile page (ID, CAA licence, POP, medical...). View still opens in the browser as before. Batch 54 also contains batch 53's upload-crash fix. Tested (8 checks, CFI + Admin, signed-out refused). | Run batch 54, open a student's paper exam and click Download. | if fix make green | working
— | 55 | Request (9 Oct 2026, screenshot of a student's folio): "I need to be able to upload an exam for a student as CFI, or delete the file and then verify pass or fail." | 9 Oct 2026 (batch 55, also inside batch 56 — not yet run) | Each exam card on the CFI/instructor's view of a student's folio now has "Upload paper exam" (or "Upload retake (paper)" after a fail). Upload the scan (PDF or photo, max 10MB; radio exam: optional licence number) and choose the result: mark later, Passed or Failed. It then shows like a student's own paper submission, so View / Download / New upload / Delete / Mark passed / Mark failed all work. Also replaces an online attempt the student opened but never answered. Tested (12 checks). | Run batch 55, open a student's folio, scroll to Exams, click Upload paper exam. | if fix mark green | working
— | 56 | Request (9 Oct 2026): "under CFI, the student and pilot list, can we make it that the order is alphabetic, sort on name". | 9 Oct 2026 (batch 56, also inside batch 57 — not yet run; includes 55) | CFI Students roster, Student profiles (Admin → Students) and Pilots now sort A–Z by name, ignoring capital letters, accents and stray spaces (before, the database sort put e.g. "Zane" above "andre"). Tested (3 checks). | Run batch 56 (it also contains batch 55), then open Students and Pilots. | if fix mark green | working
— | 57 | Request (13 Oct 2026): "under students test, if CFI verifies or reviews the exam answers, I must be able to edit and change the mark, with note, discuss, and corrected with student. If corrected it will remark and correct." | 13 Oct 2026 (batch 57, also inside batch 58 — not yet run) | On the CFI's review of an online exam, every question has "Adjust mark / add note": set the marks (0 to the question's maximum, halves allowed; blank = automatic) and a note to the student, then "Save & re-mark". The whole exam is re-marked straight away (total, %, must-pass sections, PASS/FAIL), before or after verifying. "Reset to automatic" undoes it. Works on unanswered questions too. The student sees the corrected mark and note on their results; the marked .docx shows them as well. CFI-only (instructors see notes, can't change marks). Migration 0039 (4 new columns on exam_answers). Tested (11 checks + batch 55 suite re-run). | Run batch 57, open a student's online exam review, click Adjust mark / add note on a question. | if fix mark green | working
— | 58 | Follow-up (13 Oct 2026): "I must be able to change the answer to the correct one, change the mark and also give the point; if corrected it must change the marks; if fail it must be changed to pass with the note correction." | 13 Oct 2026 (batch 58, built & delivered — not yet run; includes 55, 56, 57) | Under every question of an online exam review (CFI only): "✔ Mark correct (full marks)" in one click (answer set to the correct option, note "Corrected after review."), or "Change answer / mark / add note": pick any option as the answer, optionally override the marks, write a note. Saving re-marks the whole exam at once, so a FAIL becomes a PASS when the corrected marks reach the pass mark (verified status kept). The student's own answer is kept and shown ("Student's own answer: …"); "Undo correction" restores it. Result banner shows how many questions were corrected. Student sees "Corrected by your instructor. Your answer was: …" + note; marked .docx shows it too. Migration 0040 (original_option_id, answer_changed). Tested (12 checks). | Run batch 58, open a student's online exam, click ✔ Mark correct on a question and watch the total / PASS update. | if fix mark green | working
— | 59 | Follow-up (13 Oct 2026, screenshot of Herman Peacock, Basic Licence Theory Test FAIL 194/195 = 99.5%): "after correction, I need to pass the student. It is showing fail." | 13 Oct 2026 (batch 59, built & delivered — not yet run; includes batches 55-58) | Cause: the PG exam has a must-pass rule — every Airlaw (Section E) question needs full marks, whatever the overall %. Herman still had one Airlaw question short. Batch 59: (1) the review banner now lists the must-pass questions not at full marks, each a link that jumps to the question so the CFI can ✔ Mark correct it; (2) new CFI-only "Set final result (PASS / FAIL)" button next to Download — choose PASS or FAIL, note required (student sees it); it verifies the attempt, survives later re-marking, shows on the student's results and the marked .docx; "Back to calculated result" removes it. Migration 0041 adds 4 columns to exam_attempts. Tested: 12/12 checks + batch 58 tests 12/12. | Run batch 59 (cd C:\apex-training-portal-v20, then powershell -ExecutionPolicy Bypass -File "$env:USERPROFILE\Downloads\apex-batch59-cfi-final-result-override.ps1"). Then open Herman's exam: either click the listed Airlaw question and ✔ Mark correct, or Set final result → PASS with a note. | if fix mark green | working
Legend:
Delivered — pending your confirmation it's live/correct
Status unclear — needs your confirmation
Not started
Explicitly parked — do not build without asking

## Dev History (1-49)
Apex Flight Hub — Development History
Reference record of everything already shipped before the V22/V23/V24 lists. Line numbers match Riaan's 28 Sep 2026 renumbering. Batch column: "—" predates batch numbering (everything up to ~18 Sep 2026 shipped before batches were numbered individually).
Line No. | Batch | Description | Date Implemented | Comments | Action Required
4 | — | Deployment migrated from zip-delivery to Railway (GitHub-connected auto-deploy) — push to main triggers an automatic build/deploy. | 16-18 Sep 2026 | v20 milestone.
6 | — | Two real production accounts created on the live database, replacing seeded demo accounts: admin@apexadventures.co.za (admin), riaan@apexadventures.co.za (CFI). | 16-18 Sep 2026
7 | — | Version badge on login screen + nav footer showing version, deploy time and commit hash. | 16-18 Sep 2026 | Bumped by hand per batch. Currently reads v21.
8 | — | Delivery workflow established: single PowerShell script per batch, writes files and runs git add/commit/push. | 16-18 Sep 2026
13 | — | Full CFI exam authoring: create/edit exams, sections, questions, correct answers; +New exam form; delete-exam action; PG exam's 8 image-based diagram questions preserved. | 18 Sep 2026 | v20+ milestone. Verified end-to-end before delivery.
20 | — | Student endorsements + multi-course training type: PPG exam available to students; trainingType changed to multi-select (PG/PPG/PPT at once); CFI-granted site/skill endorsements on a student's folio (non-tiered items only). | 22 Sep 2026 | v22 milestone. Engine/Winching/XC added for PPG and PPT after initial PG-only version.
23 | 23 | Sign-up date shown on student folio next to the Start date field. | 22-23 Sep 2026 | Batch 23.
24 | 24 | Fixed 404 on "Study material" in the CFI nav — missing admin page and download route delivered. | 22-23 Sep 2026 | Batch 24.
25 | 25, 26 | Fixed page-crashing bug on "+ Add exercise" (duplicate exercise codes across the whole syllabus, not just within a section). | 22-23 Sep 2026 | Batches 25-26. Note for future work: any code catching a specific SQLite error on this app must check err.cause, not just the outer error message.
31 | — | Medical Declaration expiry (12-month, colour-coded); Consent & Indemnity doc links outside sign-up; forgot-password request flow (originally CFI/Admin-mediated only). |  | v31 milestone (exact date not on record).
32 | — | Instructor grade rating combinations: Grade C freely combines with B or A; B and A never both at once. |  | v32 milestone (exact date not on record).
33 | — | Flight/hours summaries on View profile + Logbook with a 12/24-month toggle; licence-expiry hard lock. |  | v33 milestone (exact date not on record).
34 | 34 | Submit a paper exam or an already-held SACAA radio licence for CFI/Admin review instead of writing the online exam — sits pending until marked Passed/Failed. | 25 Sep 2026 | Batch 34.
Note: this sheet is a condensed reference, not a line-by-line record of every numbered line in the source doc (many of those lines are headings or narrative text, not individual features). See the full narrative in the project doc (claude/team-apex-portal-status.md) for complete detail.